## Slide 2
2017
91 days
182 days
123 days
122 days
120 days
212 days
184 days
121 days
489 days
2020
Today
2017
2018
2019
2020
Literature Survey
Dataset Creation for x86 based system
Testing on different x86 processors and improvement
Converting into Hardware Module
Final Testing and Deliverable
Project Approval
Development of Intelligent Attacks
Design of LSTM Network
Accessing HPCs of IoT devices
Testing on different IoT devices
Survey on different types of side-channel attacks and their countermeasures
3 months
Developing different intelligent attacks to fool existing techniques
6 months
Create HPC profiler for x86 system and create dataset
4 months
Design and train an LSTM network
4 months
Improve the performance of the LSTM based on dataset for different x86 processors
4 months
Create HPC profiler for different target IoT and mobile devices
7 months
Convert the x86 based detection module to hardware module for IoT and mobile devices
6 months
Test the hardware module on different IoT devices
4 months
Final testing on both x86 processor and IoT devices and preparing final deliverable
16 months

## Slide 3
Milestone(s) | 
Date | Description
09-01-2017 | Project Approval
11-30-2017 | Literature Survey
05-31-2018 | Development of Intelligent Attacks
08-31-2018 | Dataset Creation for x86 based system
12-31-2018 | Design of LSTM Network
04-30-2019 | Testing on different x86 processors and improvement
07-31-2019 | Accessing HPCs of IoT devices
01-31-2020 | Converting into Hardware Module
05-31-2020 | Testing on different IoT devices
08-31-2020 | Final Testing and Deliverable
Task(s) |  |  | 
Duration (days) | Start Date | End Date | Description
91 | 09-01-2017 | 11-30-2017 | Survey on different types of side-channel attacks and their countermeasures
182 | 12-01-2017 | 05-31-2018 | Collecting and developing different intelligent attacks
123 | 05-01-2018 | 08-31-2018 | Create HPC profiler for x86 system and create dataset
122 | 09-01-2018 | 12-31-2018 | Design and train an LSTM network
120 | 01-01-2019 | 04-30-2019 | Improve the performance of the LSTM based on dataset for different x86 processors
212 | 01-01-2019 | 07-31-2019 | Create HPC profiler for different target IoT and mobile devices
184 | 08-01-2019 | 01-31-2020 | Convert the x86 based detection module to hardware module for IoT and mobile devices
121 | 02-01-2020 | 05-31-2020 | Test the hardware module on different IoT devices
489 | 05-01-2019 | 08-31-2020 | Final testing on both x86 processor and IoT devices and preparing final deliverable
Timeline: 09-01-2017 - 08-31-2020